## ADRs
0
ADR | Title | Description | Context | Decision | Rationale | Alternatives considered | Consequences | Old layers | Layer | Column 1
ADR-000 | EAV transpose before validation | EAV transpose before validation | Templates have dynamic columns | Convert wide→ tall before validation | One validation recipe works for any template | Template-specific validation recipes |  | Execution | Orchestration
ADR-001 | CFG tables as runtime configuration | CFG tables as runtime configuration | Validation rules change per client. | Store rules as data, not code. | Rule changes don’t require recipe deployment. |  |  | Configuration | Topology
ADR-002 | Separation of bootstrap and outreach | Separation of bootstrap and outreach | R-004 was accumulating too many concerns. | R-008 owns record creation. | Single responsibility, idempotency. |  |  | Provisioning | Orchestration
ADR-003 | Auto-versioning in R-008 | Auto-versioning in R-008. | R-008 (bootstrap) creates VER_TemplateVersion rows. The version_number field was previously hardcoded to 1, requiring manual edits for every re-publish. | R-008 queries for the highest existing version_number for the project and increments. The hardcoded version_number: 1 has been removed. | Version increments without recipe edits. Re-publishes are safe and traceable. |  |  | Versioning | Data integrity
ADR-004 | R-008 owns record creation | R-008 owns record creation. | R-004 (outreach) was accumulating responsibilities — record creation AND outreach send. Single-responsibility violations made it hard to debug and re-run. | R-008 owns all record creation for CFG/VER/WFA records and Workflow App requests. R-004 only assigns existing records and sends outreach. | Single responsibility. R-008 becomes idempotent (check-then-create); R-004 becomes a pure outreach recipe.
ADR-005 | Single validation recipe for all paths | Single validation recipe for all paths (supplier). | Multiple ingestion paths exist (file upload, manual entry, supplier portal). Each could have its own validation recipe. | One validation recipe (V-01) handles all ingestion paths. Inputs are normalized to EAV form before validation runs. | EAV transposition (ADR-000) makes the validation engine input-shape-agnostic. One recipe, one place to fix bugs.
ADR-006 | Callable recipes as internal functions | Callable recipes as internal functions. | Recipe-to-recipe communication options: webhooks (HTTP), callable recipes (call_recipe / call_recipe_async), or shared queues. Webhooks add network overhead and require URL management. | Internal recipe-to-recipe handoffs use callable recipes. Webhooks are reserved for external system boundaries (GAS → Workato, supplier portal). | Callable recipes are typed contracts and stay within the platform. No URL management, no network failure modes.
ADR-007 | Idempotent infrastructure provisioning | Infrastructure provisioning must be idempotent. | The team may re-run initialization if they have an issue. | Check-then-create pattern on every resource. | Safe to re-run. No duplicate records, no orphaned resources.
ADR-008 | Append-only execution layer | Execution layer is append-only. | RUN_* tables hold submission attempts, validation results, field errors. Mutability would lose audit history. | RUN_* tables are append-only in practice. Each submission attempt creates new records; previous attempts are preserved. | Full audit trail. Re-validations don't overwrite history. Debugging benefits — every state transition is recoverable.
ADR-009 | Workspace-level client data isolation | Client data is isolated at the workspace level. | Multi-client deployment requires data isolation. Options: per-client workspace, per-client folder/project, row-level isolation in shared tables. | Each client gets a separate Workato folder/project with its own data tables, scoped by template_project_id. Workspace-level separation only when a client requires physical separation. | Per-folder isolation provides operational separation without the overhead of separate workspaces. Row-level scoping in HOME_/base tables handles cross-client orchestration.
ADR-010 | Templates are generated artifacts, not stored assets | Templates are generated artifacts, not stored assets. | Templates change per client and per version. | Generate from CFG_Field on-demand.
ADR-011 | Asynchronous validation | Validation runs asynchronously. | Validation can take seconds to minutes for large submissions. Synchronous response would block supplier portal interactions and risk webhook timeouts. | Submission recipes (R-007/WFA-04) accept the upload, write a RUN_Upload row, and return immediately. V-01 runs asynchronously. | Suppliers see immediate confirmation of receipt. Validation runs without webhook timeout pressure. V-02 routes results when validation completes.
ADR-012 | Configurable error messages (not hardcoded) | Error messages are configurable, not hardcoded. | Different clients may require differing error language. | Store translations as data in CFG_ErrorTranslation | Error messages can be customized per client. Team can update error messages without recipe changes. SQL error codes are stable internal identifiers.
ADR-013 | Apps Script ↔ Workato communication via webhooks | Apps Script to Workato communication is driven via webhooks. | Apps Script and Workato are separate execution environments. | Workato acts as the integration boundary. | Loose coupling (either system can change internally). AS does not need to know about data table structure in Workato. Fire-and-forget (AS doesn't wait for Workato). Workato webhook URL must be stable across implementations.
ADR-014 | Environment-specific values in workspace properties | Environment-specific values live in workspace properties. | Same recipe logic runs for different clients. | Externalize all client-specific configuration. | Recipes are client-agnostic. R-008 provisions properties as part of 'bootstrap'. Properties act as runtime configuration for recipes.
ADR-015 | Incumbent data as a first-class workflow state | Incumbent data is a first-class workflow state. | Some suppliers have existing employee data to confirm or update. | Model incumbent data explicitly in WFA_SupplierRequest. | UI can branch on 'has_seeded_data' without extra queries. Seeded template can be served instead of blank one. Validation pipeline handles both seeded and blank submissions identically.
ADR-016 | Suppliers are authenticated users, not anonymous submitters | Suppliers are authenticated users, not anonymous submitters. | Supplier portal access could use anonymous magic links or authenticated user accounts. Authentication adds friction; anonymous links require careful TTL handling. | Suppliers authenticate to the WFA portal as named users. WFA_SupplierUser holds user_email; portal access is scoped by joining current_user → WFA_SupplierUser → WFA_SupplierRequest. | Audit trail per user. Multi-user-per-supplier model (ADR-033) requires named identities. Workato's WFA platform supports user authentication natively.
ADR-017 | Store file paths, not file content | Store file paths, not file content. | XLSX files can be large; data tables have known limits. | Use Workato FileStorage for binary content, data tables for metadata/file paths. UPDATE: File naming convention: {client-slug}_{variant-slug}_{version-short}_{date}.xlsx, stored under {base_path}/{client-slug}/{version-short}/. Naming is computed in the Python transform, not in the FileStorage step. | Data tables stay lean. FileStorage path becomes the reference key. File retrieval requires two steps (lookup path, fetch file) ENV_FILE_STORAGE_ROOT_ID provides root path.
ADR-018 | UI layer contains no business logic | UI layer contains no business logic. | Logic must be testable and reusable; independent of the user interface. | Controllers are thin (single line delegation pattern). | Logic lives in library functions, not menu handlers. Libraries can be updated independent of the user interface. Test harnesses can call library functions directly. Consistent with OOP patterns throught Apps Script code.
ADR-019 | Per-client configurable reminder schedule | Reminder schedule is configurable per client. | Different clients have different SLA expectations. | Expose reminder-timing as analyst-configurable field in the config file and consume it on ingestion. | No recipe changes required to adjust reminder cadence. Timing logic in recipes reads from properties or request context.
ADR-020 | Four independent lifecycle boundaries | We must maintain four lifecycle boundaries independently. | 1. Workspace lifecycle (where the implementation runs) 2. Recipe bundle lifecycle (which code/release is deployed in the workspace) 3. Business template lifecycle (which supplier-facing contract is active) 4. Request lifecycle (which version a supplier was asked to fulfill) |  |  |  |  | Architecture | System boundary
ADR-021 | Collapse Apps Script to thin webhook trigger | Reduce Google Apps Script from full provisioning control plane to a minimal, menu-driven webhook trigger. The entire backend (ProvisioningRunner, InventoryService, WorkatoClient, FleetManager, RegistryService, ManifestService, AppContext) is deprecated. What remains is onOpen() --> menu item --> read Sheet --> validate --> fire UrlFetchApp.fetch() --> toast | The original GAS backend was a web app (doPost) that authenticated inbound calls, checked out workspaces froma fleet registry in Google Sheets, provisioned Workato data tables and env props via Workato Developer API, tracked sate, generated unique IDs, and fired a 'bootstrap' webhook call. This worked, but it stretched authority across two systems (GAS coauthed entity identities, managed fleet state, and maintained it's own manifest cache. The 401 authentication errors debugged (traced to regional ep routing and incorrect API paths) were a symptom of this split. | (1) GAS's only job is to originate requests. The Sheet becomes stateless. (2) GAS also derives a `_field_visibility` map from `7_form` during serialization (field name → boolean). This is a pure extraction (no business logic), and consistent with the thin-trigger principle. | The one advantage to using GAS was that it lived within Google Workspace (native Sheet/Drive access, user-context auth, menu items). However, Workato can do most of these things without an extra hop. | (1) Keep GAS as a think pass-thru w/doPost: Still requires web app deployment, auth. Trigger is a Sheets menu action, not inbound webhook, doPost serves little purpose. (2) Eliminate GAS entirely. Have Workato poll Sheets or use Google Forms trigger: Loses native Sheets UX (menu items, toast, input validation before submit). |  |  | System boundary, Integration
ADR-022 | Workato home base project as control plane | Designate a single Workato project ("base") as the control plane for all provisioning, routing, registry, versioning, and cross-client operations. The project should contain the webhook endpoint, three data tables (WorkspaceRegistry, Requests, Manifests), five orchestration recipes, manifest file in FileStorage, template recipe bundle, connector with business logic. | Authority over the platform was split. GAS owned fleet assignment, idempotency checking, manifest hashing, bootstrap orchestration, and Workato owned per-client runtime. This created a co-authoring problem; GAS pre-generated IDs, sent them to Workato, then persisted the response mappings back to the Sheet. | Workato owns both orchestration and runtime. The base workspace/project is the single point of entry (via webhook), the single source of truth re fleet state, request lifecycle, template versioning. | (1) Workato can query data tables without a (noticable) API hop. Registry lookups, idempotency checks, manifest reads, become trivial. (2) All business IDs are generated by the recipe that creates the row (convention: UUID, never generated upstream. (3) Version freezing happens in a single system. There is no opportunity for GAS and Workato to disagree about which version is active. (4) The base project is deliberately thin. | (1) Hybrid control plane (GAS + Workato): This was the status quo. Reject because it required maintaining state in two palce and the handoff had become the source of most bugs. (2) External orchestrator (Cloud function, Lambda): Adds infrastructure outside of both systems. Workato already has callable recipes, data tables, webhook triggers. An external orchestrator does not add capability, just complexity. | - 3 data tables in base project - Google Sheets fleet registry deprecated - Recipe-to-recipe handoffs within Workato replace GAS-to-Workato webhook chains. |  | Orchestration, Topology
ADR-023 | Single workspace with a multi-workspace seam | Build for case A (all client folders in a single Workato workspace), while designing the abstraction that makes case B (multi-workspace) a routing-only change. | The platform needs per-client isolation (each client gets its own folder with its own tables, recipes, and Workflow App). Today, one workspace is sufficient. In the future, workspace splits may be needed for capacity, regional data residency, or client security requirements. The original GAS backend had fleet management (FleetManager, RegistryService) that was tightly coupled to the provisioning flow, and splitting workspaces would have required rewriting multiple systems. | WorkspaceRegistry exists in the base project with one row today. The webhook payload includes workspace_id as a reserved field (null/ignored for now). R-1b (Route Request) is a near-passthrough today but is the designated insertion point for routing logic. When multi-workspace is needed, R-1b reads workspace_id from the request or from a routing rule, and dispatches to the appropriate workspace's bootstrap recipe via its API. The per-project bootstrap logic (R-2a) and everything downstream stays identical. | (1) The cost of the abstraction today is near-zero: one Data Table row, one passthrough recipe, one reserved payload field. (2) The future migration is additive; add a routing decision to R-1b, register new workspaces in WorkspaceRegistry. No changes to Apps Script, no changes to per-client recipes. (3) WorkspaceRegistry.api_endpoint and api_token_ref (a property name, never the actual token) are the only fields needed to address a remote workspace. | (1) Build multi-workspace now: Premature. One workspace handles current load. The abstraction boundaries are in place; the implementation can wait. (2) No abstraction, retrofit later: Cheaper today, expensive later. R-1b as a routing seam costs almost nothing. | (1) R-1b exists even though it's currently a passthrough. This is intentional. (2) WorkspaceRegistry has fields (api_endpoint, max_capacity) that are unused in Phase 1. |  | Topology
ADR-024 | correlation_id as a universal tracing key | A single UUID, generated by Apps Script at webhook time, threads through every recipe handoff, every Data Table entity, and every Workato API call header (x-correlation-id) for the lifetime of a data collection request. | The original system had multiple IDs serving overlapping purposes: workspace_binding_id (fleet tracking), bootstrap_id (provision tracking), template_project_id (business entity), and various generated UUIDs written to _runtime_state. Tracing a failure required correlating timestamps across GAS logs, Workato job history, and Sheet state (none of which shared a common key). | Apps Script generates one UUID (Utilities.getUuid()), sends it as correlation_id in the webhook payload. R-1 writes it to Requests. Every downstream recipe passes it on handoff. It's stamped on WFA_TemplateProject.correlation_id and WFA_SupplierRequest.correlation_id in the per-client project. Workato's platform logs tie API call failures to it via the x-correlation-id header. GAS logs it at send time. | (1) One key spans the full chain: GAS log → Workato webhook trigger → recipe job history → Data Table records. (2) Idempotency becomes a simple check: R-1 queries Requests for existing correlation_id before creating a duplicate row. Double-clicks and retries are handled. (3) workspace_binding_id is absorbed (the correlation_id serves the same function now that Workato owns both assignment and provisioning). | (1) Separate client_id and correlation_id: Adds a concept without adding value. Collapsed to one ID. (2) Stamp correlation_id on every entity (including RUN_Upload, RUN_FieldError): Considered and deferred. The hop from RUN_Upload.supplier_request_id → WFA_SupplierRequest.correlation_id is short enough. Denormalization can happen later if cross-client reporting demands it. | (1) Every recipe's input schema includes correlation_id. (2) Every callable recipe handoff passes it explicitly. (3) The webhook contract is the origin (no server-side generation of the tracing key). |  | Cross-cutting
ADR-025 | Five-point version chain of custody | Template version identity is frozen at five discrete points in the recipe chain. Each freeze copies the version reference from the upstream entity (therefore, it's inherited, never looked up from a "current" flag). | The original system had a mutable current_version_id field on WFA_SupplierRequest that stored internal Workato record IDs instead of business UUIDs (RISK-01 from the data model analysis). This meant a version change could silently affect in-flight supplier requests. There was no documented chain showing which recipe froze which field or when. | The chain is: (1) R-2a stamps manifest_id on Requests → ties the entire client project to a specific manifest version. (2) R-2b creates VER_TemplateVersion with status = published → all CFG_* rows are hydrated against this version; it's immutable after publish. (3) R-008 stamps assigned_version_id on each WFA_SupplierRequest → ties each supplier to the published version. (4) R-007a copies template_version_id from WFA_SupplierRequest.assigned_version_id onto RUN_Upload → inherited, not looked up. (5) R-002 copies template_version_id from RUN_Upload onto RUN_ValidationResult → direct traceability, immutable. All status fields are forward-only. No rollbacks. | (1) Copy-forward means no recipe ever reads a "current" pointer that could change between write and read. Version drift is structurally impossible. (2) Each freeze point is owned by exactly one recipe, making debugging unambiguous: if RUN_ValidationResult has the wrong version, R-002 is the only place to look. (3) The chain is auditable: given any RUN_ValidationResult, you can walk backward through the chain to the original manifest. | (1) Single version stamp at provisioning time, all downstream reads from one location: Simpler but fragile. A lookup-based approach means any concurrent version change (publish v2 while v1 suppliers are active) silently corrupts in-flight data. (2) Version column on every table: Overkill. The chain already provides traceability; denormalizing to CFG_* rows would add write cost without adding query value. | Once R-008 has frozen assigned_version_id on any WFA_SupplierRequest, the CFG_* rows scoped to that version must not change. Immutability is a convention enforced by recipe logic, not by Workato platform constraints. UPDATE 1: Spreadsheet-minted UUIDs (_pk_fields_) are informational only; no downstream system consumes them. Authoritative IDs are minted at publish time, scoped to template_version_id. UPDATE 2: Status gate: WFA_SupplierRequest.status transitions from 'pending' to 'in_progress' on first supplier touch. Re-publish only re-stamps pending records; in-progress and beyond are frozen to their assigned version." |  | Data integrity
ADR-026 | Split R-2a and R-2b | Provisioning is split into two callable recipes: R-2a (Provision Client Folder) handles infrastructure (13 tables, deferred relations, recipe cloning, rebinding, Workflow App setup, and bookkeeping). R-2b (Parse & Hydrate Config) handles business data — pulls the config spreadsheet from Drive, parses each sheet, hydrates CFG_* tables and VER_TemplateVersion, and publishes the version. | R-2a was already the heaviest recipe in the system (13 table creates, 3 deferred relations, 5 recipe clones, Workflow App setup). Adding sheet-by-sheet config parsing (7 sheets, each with different schemas and cross-references) would create a 25+ step monolith that's nearly impossible to debug when step 19 fails. | R-2a creates the infrastructure; R-2b populates it with business data. R-2a calls R-2b at its final step, passing request_id, correlation_id, project_folder_id, table_results_map, config_file_id, and template_file_ids. Both live in the base project (not the client folder) because they run once during provisioning and need Drive access. | (1) If config parsing fails, R-2a already succeeded (the client folder exists with valid but empty tables). R-2b can be re-run without reprovisioning infrastructure. (2) Each recipe has a clear responsibility: R-2a is IaC, R-2b is data hydration. Debugging is scoped. (3) R-2b replaces what was previously an entirely manual and undocumented configuration phase (C-1 through C-7). Making it a separate recipe makes the automation explicit and testable in isolation. | (1) Monolithic R-2a: Rejected for debuggability and partial-failure recovery reasons. (2) R-2b in the client folder: Rejected because it needs Drive access for the config file and runs once during provisioning (it's an orchestration concern, not a runtime concern). | (1) The full provisioning chain is now: R-1 → R-1b → R-2a → R-2b → R-008. Five recipe hops from webhook to operational client folder. (2) table_results_map (the bridge between R-2a's table creation and R-2b's data hydration) must be serialized and passed between recipes. |  | Topology, System boundary
ADR-027 | Config file as source of truth, parsed once | The master config spreadsheet (Google Sheets) is the single source of truth for field definitions, validation rules, lookups, variants, suppliers, and users. Apps Script generates XLSX templates from it. The webhook carries a pointer (config_file_id) to the config file; Workato pulls and parses it once during provisioning (R-2b), writes the parsed JSON to FileStorage, and stores the parsed_config_file_id on WFA_TemplateProject. Downstream recipes (R-008) read from FileStorage, not from Drive. | In the v2.0.0 design, both R-2b and R-008 pulled from Google Drive — R-2b to hydrate CFG_* tables, R-008 to parse supplier/user sheets. This meant two Drive round-trips, two parse passes, and a runtime dependency on Drive availability for the client-folder recipe. | R-2b parses the config once, writes the full parsed JSON to FileStorage, and stores the FileStorage ID on WFA_TemplateProject.parsed_config_file_id. R-008's input changes from config_file_id to parsed_config_file_id. R-008 reads from FileStorage — no Drive dependency. | Parse once, read many. The config file is frozen at provisioning time; re-parsing it is wasted work. Client-folder recipes should not depend on external systems (Google Drive) that the base project's orchestration layer already accessed. The FileStorage artifact is internal to Workato and always available. The parsed JSON artifact is auditable — it captures exactly what configuration was active at provision time, independent of subsequent Sheet edits. | (1) Embed config in the webhook payload: The config can be large (hundreds of lookup values, dozens of fields). The webhook stays lean; heavy data is pulled, not pushed. (2) Both R-2b and R-008 pull from Drive (v2.0.0): Works but creates an unnecessary external dependency for R-008 and duplicates parse logic. (3) Store parsed config in a Data Table column: Data Tables have cell size limits. FileStorage handles arbitrary JSON size cleanly. | (1) WFA_TemplateProject gains parsed_config_file_id (schema v3.1.0). (2) R-008 has no Google Drive dependency. (3) The parsed config JSON in FileStorage is an auditable artifact tied to the correlation_id. |  | Integration, Data integrity
ADR-028 | Multi-user supplier model | Portal access is decoupled from supplier request identity. WFA_SupplierRequest represents a supplier-level engagement (one per supplier per data collection cycle). WFA_SupplierUser represents an individual person who can access the portal and upload files on behalf of that supplier. | The original model used WFA_SupplierRequest.contact_email as both the outreach target and the portal access key. This assumed one person per supplier. Real-world usage shows multiple people at a single supplier (e.g., a primary contact and a delegate) need portal access and upload capability. | contact_email stays on WFA_SupplierRequest as the primary contact for outreach emails (R-004). Portal access is scoped by WFA_SupplierUser.user_email. The Workflow App scoping filter changes from contact_email = current_user to a join: WFA_SupplierUser.user_email = current_user → supplier_request_id → WFA_SupplierRequest. R-008 creates both WFA_SupplierRequest and WFA_SupplierUser rows, with the first user's email copied to contact_email. | (1) Separates two concerns that were conflated: "who do we email about this request?" vs. "who can log in and upload files?" (2) The config already supports this (sheet 3_users has multiple rows per supplier). The data model now matches the config structure. (3) R-007a's logic doesn't fundamentally change (the Workflow App still scopes to the right supplier request; it just resolves through one extra hop). | (1) Comma-separated emails on contact_email: Fragile, breaks email sends, makes Workflow App scoping a string-parsing problem. (2) Defer until multi-user is actually needed: The config sheet already has the data. Building the table now avoids a schema migration when a client first has multiple users per supplier. | (1) Per-client table count goes from 10 to 13 (including WFA_SupplierUser, CFG_Variant, CFG_VariantField). (2) WFA_SupplierUser → WFA_SupplierRequest is a deferred relation (resolved in R-2a Pass 2). (3) Workflow App configuration requires a join-based scoping filter. |  | Domain model | Task assignment
ADR-029 | Manifest based IaC versioning | Recipe R-00 (Package & Version) snapshots the current template project definition (recipe bundle and table schemas) into a versioned manifest stored in the Manifests Data Table. Each snapshot produces a manifest_id, manifest_hash (SHA-256 of the canonical snapshot), and schema_version. Only one manifest row has is_current = true at any time. R-2a reads the current manifest at provision time and stamps its manifest_id on the Requests row. | The original system had no deployment versioning. There was no tracking of which recipe bundle or schema version was deployed to a given workspace. Drift detection was schema-only (via InventoryService._updateTableSchemaIfChanged), not behavior-aware. The GAS ManifestService built a SHA-256 hash for idempotency, but it hashed the request payload, not the template definition. | R-00 runs on schedule or manual trigger. It snapshots the template project (table schemas from the data table manifest, recipe definitions), computes a canonical hash, and writes a Manifests row. The is_current flag is flipped atomically (old row false, new row true). Provisioning always reads the current manifest, so every client folder is traceable to exactly one manifest version. | (1) Every client folder is bound to a specific manifest at provision time. No ambiguity about what schema or recipe version a client was provisioned with. (2) The hash enables idempotency: identical template definitions produce the same hash, so R-00 can skip a write if nothing changed. (3) The snapshot in FileStorage is an auditable artifact (you can reconstruct what any client was provisioned with by reading their manifest_id). | (1) Use Workato's native project export/manifest: Workato doesn't expose a versioned manifest API that covers table schemas + recipe definitions in a single snapshot. The custom approach is more complete. (2) No versioning, always provision from live template: Makes it impossible to know what version a client is running when the template changes. | (1) R-00 must run (and succeed) before any provisioning. If Manifests has no is_current = true row, R-2a fails with a clear precondition error. (2) Schema changes to the template require an R-00 run before they affect new clients. |  | Data integrity
ADR-030 | Webhook contract design (lean payload, pointers not data) | The webhook payload from Apps Script to R-1 carries six fields: correlation_id, client_name, analyst_email, target_vms, config_file_id, template_file_ids, and timestamp. Heavy data (field definitions, rules, lookups, suppliers, users) lives in the config spreadsheet and is pulled by Workato, not pushed through the webhook. | The original backend sent provisioning payloads that included all supplier data, generated business IDs, and metadata. The payload was the contract between two systems, and it grew as the system grew. | The webhook is a "please provision this client" request with pointers, not data. config_file_id is the Google Drive file ID of the master config spreadsheet. template_file_ids is an optional array of {variant_name, file_id} pairs for pre-generated XLSX templates. Everything else is derived by Workato from the config file. | (1) Lean payloads are debuggable. Six fields fit in a log line. (2) The config file is the source of truth. Duplicating its contents in the webhook creates a synchronization problem (what if the Sheet changed between payload construction and webhook delivery?). (3) Workato reads the config at parse time (R-2b), creating a point-in-time snapshot. The webhook doesn't need to carry that snapshot. | (1) Full payload with all config data embedded: The original approach. Rejected because it made the webhook contract brittle and the payload large. (2) No template_file_ids, let Workato find them in Drive: Possible but adds a Drive search step that GAS already resolved. The pointer is cheap to include. | (1) Apps Script must ensure config_file_id is a valid, accessible Drive file ID before sending. (2) R-2b must handle Drive access failures gracefully (the config file could be deleted or permissions changed between webhook send and parse) |  | Integration
ADR-031 | SDC platform connector for domain logic | A custom Workato connector ("SDC Platform Connector") encapsulates domain-specific operations: parse config, validate config, validate upload, and generate report. Referenced in the base project's assets. | Complex operations like config parsing (7 sheets, cross-referencing fields/lookups/rules), upload validation (applying field rules, lookup checks, cross-field validations), and report generation (translating field errors into human-readable output) don't map cleanly to Workato's built-in actions. Embedding this logic directly in recipe steps would create unmaintainable recipes with dozens of inline scripts. | Domain logic that is complex, reusable, and version-sensitive lives in a custom connector. Recipes call connector actions like any other Workato action. The connector is versioned alongside the platform. | (1) Custom connectors are testable in isolation, versioned, and reusable across recipes. (2) Recipe builders work with clean action interfaces (input schema, output schema) rather than inline Ruby/Python scripts. (3) The connector boundary separates "what to do" (recipe orchestration) from "how to do it" (parsing, validation, report generation). | (1) Inline scripts in recipes: Works for simple logic but becomes unmaintainable for multi-sheet config parsing or multi-rule validation. (2) External microservice (Cloud Function): Adds infrastructure outside Workato. The connector runs inside Workato's execution environment with native access to Data Tables and FileStorage. | (1) Connector updates require testing against the current manifest schema. (2) The connector's action interfaces become part of the platform's API contract. Design conventions: (DC-1) All select/pick_list fields include toggle_field blocks for pill-mappable flexibility. The type attribute is omitted from the parent field when toggle_field is present (Workato SDK constraint). (DC-2) Connector actions report facts (e.g., form_field_limit exceeded → warn); recipes enforce policy (e.g., gate and return error). This separation allows different recipes to apply different thresholds. |  | Topology, Integration
ADR-032 | Automated configuration phase | The previously manual and undocumented configuration phase (seven steps from "create template version" through "publish version") is now fully automated by R-2b. The analyst's workflow ends at "click the menu button" (step A-10). Everything from there is automated: R-1 → R-1b → R-2a → R-2b → R-008. | Between provisioning (R-2a creates the folder and tables) and bootstrap (R-008 creates supplier requests), there was an entire manual workflow where someone had to create a template version, define fields, define rules, populate lookups, configure variants, set up error translations, and publish the version. This was undocumented in v1 and error-prone; any missed step left the client folder in a partially configured state. |  | (1) Eliminates the most error-prone phase of the workflow. The analyst defines everything in a familiar environment (Google Sheets) and the system handles the rest. (2) The analyst workflow (A-1 through A-11) is now fully documented in the system manifest's configuration_phase section. (3) Automated hydration is deterministic and auditable (the parsed config JSON in FileStorage captures exactly what was applied). | (1) Keep manual configuration with better documentation: Documentation doesn't prevent human error. Automation does. (2) Build a Workato Workflow App for analyst configuration: Possible but premature. Analysts are already comfortable in Sheets. The Sheets→webhook→automation pipeline is working. | (1) Config validation before publish becomes important: R-2b should verify that every CFG_Field with a lookup_name has corresponding CFG_Lookup rows, every CFG_Rule references valid field IDs, etc. This is an open design question (noted in the manifest). (2) Re-triggering the webhook after config edits raises a versioning question: create a new VER_TemplateVersion (v2) or reject the request? The forward-only status convention suggests a new version is correct — suppliers already bootstrapped on v1 stay on v1. |  | Orchestration
ADR-033 | Client folder self-containment | Each client folder (SDC_{client_name}_{correlation_id_short}) is fully self-contained after provisioning. It holds 13 Data Tables, 5 recipes, and a Workflow App (i.e., everything needed to operate a complete supplier data collection cycle without reaching back to the base project). | The base project owns orchestration; the client folder owns operations. The boundary between them is provisioning (i.e., once R-2a/R-2b/R-008 complete, the client folder is independent). | After provisioning: (1) Client-folder recipes (R-008, R-004, R-007a, R-002, R-006) read only from their own tables. (2) The Workflow App binds to three client-local tables (WFA_SupplierRequest, WFA_SupplierUser, RUN_Upload). (3) No client-folder recipe calls back to the base project or reads from home base tables. (4) The base project updates Requests.status = ACTIVE and provisioned_at as its final act; after that, it's uninvolved. | (1) Isolation simplifies reasoning: anything about a specific client is inside one folder. (2) Failure isolation: if one client folder's recipe errors, no other client is affected. (3) Future workspace migration: a self-contained folder can theoretically be moved to another workspace without changing internal recipe logic. | (1) Shared lookup tables across clients: Saves some duplication (e.g., common error translations) but creates cross-client coupling. Rejected for isolation. (2) Client recipes query base project for config updates: Breaks the version-freezing model. Config is frozen at provisioning time. | (1) Any cross-client operation (reporting, monitoring, alerting) lives in the base project, not in client folders. (2) Schema updates to the template require re-provisioning (or a dedicated migration recipe); they don't propagate automatically to existing client folders. |  | Topology, System boundary
ADR-034 | Field visibility is authored in the spreadsheet (config file), derived in the pipeline (Workato) | The 7_form tab is the single source of truth for which fields appear on the manual-input form. GAS extracts a flat _field_visibility map (field name → boolean) and includes it in the serialized JSON. The connector's Parse Config action merges visibility onto each parsed field record as a "visible" boolean. | The Workflow App manual-input form needs to know which fields to render, but the form's field pool is fixed at design time. The analyst needs a way to curate the form surface area from within the spreadsheet they already use for all other config. | Visibility is authored as checkboxes in 7_form (one per field from 4_fields). GAS serializes this as a derived _field_visibility key in the config JSON. Parse Config merges it onto each field record. Downstream consumers read the "visible" boolean — they never parse the raw 7_form 2D array. | The analyst owns the "which fields?" decision in a familiar UI (checkboxes). The system owns the "how to represent it?" decision. GAS stays thin (pure extraction). The connector is the single merge point. Backward compatible — if _field_visibility is absent (older GAS), all fields default to visible. | (1) Add a "visible" column directly to 4_fields: Mixes concerns — 4_fields defines field attributes, 7_form defines form behavior. Also, 4_fields already has 19 columns. (2) Let the connector parse 7_form's raw 2D array: Moves spreadsheet layout knowledge into the connector. The derived map keeps the connector layout-agnostic. | (1) 7_form is included in CONNECTOR_SHEETS and serialized in the JSON payload. (2) _field_visibility is a derived key (underscore prefix convention) alongside raw sheet data. (3) coerceTruthy in GAS matches coerce_boolean in the connector for consistent boolean handling.
ADR-035 | Form field extraction as a separate connector aciton | Extract Form Fields is a standalone action in the SDC Platform Connector. It accepts parsed fields and lookups from Parse Config, filters to visible fields, resolves control types, and returns only the lookups the form needs. | Parse Config answers "what does the config say?" Validate Config answers "is it consistent?" C-01 also needs "what does the form need?" — a consumer-specific projection of the parsed data that filters, derives, and scopes. | A new action (extract_form_fields) rather than extending Parse Config. Accepts field_definition and lookup_definition arrays as input (reusing existing object definitions). Returns form_fields (with control_type resolved), lookup_tables (scoped to visible fields only), and a summary. | Each action has a different consumer and a different reason to change. Parse Config is called by any recipe that needs structured config. Extract Form Fields is called only by recipes that provision form UI. Independently testable in the SDK panel. | (1) Add form-specific fields to Parse Config output: Bloats the action for consumers that don't need form data. Violates single responsibility. (2) Derive control types in recipe formulas: Scatters mapping logic across recipes. Not testable in isolation. | (1) C-01 calls three connector actions in sequence: Parse Config → Extract Form Fields → (later) Validate Config. (2) The form_field object definition is a deliberate subset of field_definition — only form-relevant properties. (3) lookup_tables output is pre-scoped, eliminating filtering in downstream steps.
ADR-036 | Control type derived from data type and data format | The resolve_form_control_type method in the connector maps data_type + data_format to a form control string (text, number, email, date, select, dependent_select, checkbox, currency). Data format takes precedence where it implies a specific control. | The analyst declares data type and format in 4_fields. The Workflow App form needs to know what kind of input control to render. This mapping is deterministic and should not require the analyst to specify a third attribute. | Control type is derived, not authored. The mapping lives in the connector as a pure function. data_format is checked first (e.g., "email address" → email regardless of data_type), then data_type is the fallback. | The analyst shouldn't specify redundant information. The derivation is a pure function of two existing inputs. Keeping it in the connector means it's versioned, testable, and consistent across all consuming recipes. | (1) Add a "control_type" column to 4_fields or 7_form: Redundant with data_type + data_format. Creates a synchronization problem if the analyst changes data_type but forgets control_type. (2) Derive in Python (Step 10): Works but scatters domain logic outside the connector. | (1) control_type is stamped onto CFG_Field records during the Python transform (Step 10). (2) If the mapping needs to change (e.g., new control type), only the connector method needs updating. (3) Backfillable: existing CFG_Field records can have control_type derived retroactively.
ADR-037 | Fixed slot pool with config-driven assignment | The Workflow App form uses a pre-provisioned pool of 20 generic input slots (8 text, 2 number, 4 date, 4 select, 2 boolean), each with a companion label column. Visible fields are assigned to slots by control type at publish time. Assignments are written to CFG_FormSlot. | Workflow App form fields are bound to data table columns at design time — they cannot be dynamically created at runtime. The platform imposes a practical ceiling on the number of dynamic fields. The system needs to bridge a config-driven field model with a fixed-schema form. | A slot pool pattern: pre-provision typed slots on WFA_SupplierRequest (slot_text_01 through slot_bool_02, plus corresponding _label columns). The Python transform (Step 10, Phase 7) assigns visible fields to the next available slot of the matching type. CFG_FormSlot records the assignment for runtime lookup. Slot names use the slot_ prefix for visual distinction. | (1) Deterministic assignment (sorted by position, first-available within type pool) is reproducible and debuggable. (2) The label column pattern gives the form self-describing fields — the form reads labels from the request record, not from a join. (3) Type-bucketed pools prevent a text field from consuming a date picker slot. | (1) Single pool of 20 generic text slots: Loses type-appropriate input controls. Every field becomes a text box. (2) Dynamic form rendering via custom UI: Not supported by Workflow Apps. (3) One WFA form per client: Doesn't scale — each client would need a custom Workflow App. | (1) WFA_SupplierRequest gains 40 columns (20 value + 20 label). All strings. (2) CFG_FormSlot is a new data table (version-scoped, populated during C-01). (3) Pool sizing (8/2/4/4/2) is a tunable parameter. If a config exceeds a type bucket, slot_warnings surfaces the overflow. (4) The form_field_limit in Extract Form Fields and Validate Config must match the total pool size.
ADR-038 | Slot metadata denormalized into supplier request records | Each WFA_SupplierRequest record carries the full set of slot label columns (e.g., slot_text_01_label = "Employee name"). The form reads these labels to determine which slots are active, how to label them, and whether to show them. Unassigned slots have null labels, which drives conditional visibility. | The Workflow App form builder binds directly to data table columns. It cannot perform joins to CFG_FormSlot at render time. Each supplier's form layout must be resolvable from the request record alone. | Denormalize slot metadata onto WFA_SupplierRequest at bootstrap time (Step 49). The Python builds a slot_columns dict (all 40 columns initialized to null, then labels stamped from cfg_form_slots) and spreads it onto each supplier request record. | (1) The form is self-contained per supplier, per version. No runtime joins. (2) Version-pinning comes for free: each supplier's labels are frozen at the version they were assigned. Re-publish stamps new labels only on pending records. (3) The slot_columns spread is computed once and applied to all suppliers on the same version. | (1) Form reads from CFG_FormSlot via lookup: Not supported by Workflow App form binding. Would require a bot recipe to hydrate the form on page load. (2) Store labels in a separate WFA_FormMetadata table, one row per slot per supplier: Cleaner normalization but adds a table and a query per form render. The denormalized approach is simpler for the Workflow App's constraints. | (1) WFA_SupplierRequest is wider (40 extra columns) but the columns are sparse (most null). (2) Re-publish logic must re-stamp labels on pending records and leave non-pending untouched. (3) The un-mapping step (slot → field name) at submission time reads CFG_FormSlot to reverse the assignment.
ADR-039 | Re-publish 'stamps' pending records, freezes those in progress | When the team publishes an updated configuration, C-01 creates a new template version with new CFG_* records. Pending WFA_SupplierRequest records are re-stamped with the new versions slot layout. Records that have transitioned to 'in progress' (or beyond) are 'frozen' (i.e., version, slot labels, form layout is all immutable). | The team reports that they frequently update configurations after initial publish (adding fields, changing visibility, adding suppliers). The system must apply changes to suppliers who haven't started yet without disrupting suppliers who are mid-entry. | The ELSE branch of C-01's bootstrap conditional (Steps 52-56) queries all WFA_SupplierRequest records for the project. Pending records are re-stamped with the new assigned_version_id and updated slot labels. Non-pending records are untouched. New suppliers (present in config but absent from request records) get fresh records. Detection compares against all statuses to avoid duplicate creation. | (1) Prevents mid-flight disruption. A supplier actively entering data sees a stable form. (2) The status field is the single gating mechanism — no separate ""locked"" flag needed. (3) New supplier detection against all statuses (not just pending) prevents duplicates for suppliers who are already in_progress. | (1) Never update existing records, always re-bootstrap all suppliers: Destructive. Loses any partial data or status history. (2) Add a separate "config_locked" flag: Redundant with status. The lifecycle state already encodes whether the record is mutable. (3) Require analysts to create a new project for config changes: Too rigid. Minor field visibility changes shouldn't require a full re-provision. | (1) Step 54 must query all request records (not just pending) to support new-supplier detection. (2) The re-stamp Python (Step 55) uses the same slot_columns logic as the initial bootstrap (Step 49), ensuring consistency. (3) The status transition from pending → in_progress must be triggered reliably (form open or template download) to prevent accidental re-stamping.
ADR-040 | Configuration update reuses the 'front door' | Config updates (analyst changes the config workbook after initial provisioning) and initial provisioning use the same webhook endpoint. R-1 detects the difference by looking up config_file_id in the Requests table — if an ACTIVE row exists, it's an update; if not, it's new. | Config updates need a trigger mechanism. Options: a separate webhook endpoint, a WFA page action, or the same webhook used for initial provisioning. Each adds different surface area, separate validation paths, and per-trigger documentation. | The analyst fires the same GAS webhook for both initial provisioning and config updates. - New request path: R-1 → R-1b → R-2a → R-2b(is_initial=true) → R-008 - Update path: R-1 → R-1b → R-2b(is_initial=false) — skips R-2a and R-008 Detection is by config_file_id, not correlation_id (which GAS regenerates per webhook fire). | One entry point, one payload shape, one validation step. The analyst's workflow is identical — edit the config, click the button. The routing logic is a single DB lookup that already happens in R-1. A separate endpoint would duplicate webhook handling and validation for no benefit. | (1) Separate webhook endpoint per operation: Doubles the GAS surface area and the Workato intake surface. Two contracts to maintain. (2) WFA page action: Requires the analyst to leave Google Sheets and navigate to Workato. Worse UX for a flow that's otherwise spreadsheet-native. | (1) R-1 must perform a config_file_id lookup against Requests on every webhook. (2) R-2b takes an is_initial boolean parameter that gates the R-008 call. (3) GAS continues to generate a fresh correlation_id per webhook — it cannot serve as the idempotency key. |  | Orchestration, System boundary
ADR-041 | R-2b stays in the base project | R-2b (Parse & Hydrate Config) lives in the base project, not the client folder. It uses the Data Tables API connector for dynamic table addressing (table_id from table_results_map) instead of the standard Data Tables connector. | Most per-client recipes are cloned into client folders by R-2a. R-2b is called by both R-2a (initial provisioning) and R-1b (config update path). Workato's call_recipe_async requires a static flow_id at design time. A client-folder recipe's flow_id is only known after R-2a clones it, which makes it unaddressable from R-1b. | R-2b lives in the base project. Both R-2a (initial) and R-1b (update) call it as a known, static flow_id. Dynamic table access uses the Data Tables API connector with table_id resolved from table_results_map. | Both callers can reference one stable flow_id. The Data Tables API connector makes dynamic table access possible without per-client recipe copies. Keeping one R-2b also means parsing/hydration bug fixes apply to all paths simultaneously. | (1) Clone R-2b into each client folder: Solves the static-binding problem for R-2a's call but breaks R-1b's call (the update path doesn't run R-2a, so there's no recently cloned recipe to address). (2) Two parallel hydration recipes (one in base, one in client folder): Duplicate code paths drift. Rejected by AD-26. | (1) R-2b must use the Data Tables API connector, which has a different schema than the standard Data Tables connector. (2) R-2b is the only base-project recipe that performs heavy data writes against per-client tables. (3) table_results_map must be passed in on every call (R-2b cannot infer it). |  | Topology, System boundary
ADR-042 | One hydration recipe for all versions (monolithic R-2b) | R-2b is the single recipe responsible for parsing the config, validating it, creating a new template version, hydrating CFG_* tables, and storing the frozen config snapshot. It handles both initial provisioning and config updates. | Initial config hydration and config updates perform the same logical operation — parse config, validate, create version, write CFG rows, store frozen config. Only two things differ: version number (always 1 for initial; previous + 1 for update) and whether R-008 is called afterward. | R-2b handles both paths. An is_initial boolean parameter controls the R-008 gate. Version deprecation (Steps 4–7) is a no-op on first run because no published version exists yet. | One recipe, one code path, one place to fix parsing bugs. The is_initial flag is a single if/else — the cost of two separate recipes (with duplicated logic that drifts) far outweighs the cost of one boolean branch. | (1) Two separate recipes (R-2b-initial and R-2b-update): Duplicate parsing logic. Bug fixes must be applied twice; drift is inevitable. (2) R-2b-update inherits from R-2b-initial: Workato has no recipe inheritance. The only mechanism is copy-paste. | (1) R-2b's complexity is concentrated in one place — high leverage but also high blast radius. (2) The is_initial parameter becomes part of R-2b's contract and must be set explicitly by every caller. (3) Version-deprecation steps run unconditionally; they're no-ops on first invocation. |  | Orchestration
ADR-043 | Version scoping, not deletion | When a config update creates a new version, old CFG rows (CFG_Field, CFG_Rule, CFG_Lookup, CFG_ErrorTranslation, CFG_Variant, CFG_VariantField) are never deleted. Each hydration creates new rows scoped to a new template_version_id. Old rows become inert when their version's status changes to deprecated. | When a config update creates a new version, the old version's CFG rows need to be handled. Options: delete old rows, or leave them scoped to the old version. | Old CFG rows are never deleted. Each hydration creates new rows scoped to a new template_version_id. The old version's rows become inert when its status changes to deprecated. | (1) Preserves full audit trail — you can always see what a supplier was validating against at any point. (2) Enables potential rollback (re-activate old version without re-parsing). (3) Deletion is destructive and irreversible; scoping is additive and safe. (4) Existing in-flight supplier requests that reference the old version continue working without recipe changes. | (1) Delete old CFG rows on version supersession: Loses audit trail. Breaks any in-flight supplier still validating against the old version. Irreversible. (2) Soft-delete via is_active flag: Adds a column without adding capability over template_version_id scoping. | (1) CFG_* tables grow monotonically. Volume isn't a concern at current scale; revisit if/when row counts require it. (2) All CFG reads must filter by the consuming entity's frozen template_version_id, never by 'current' or 'is_active'. (3) Querying historical configs is a date- and version-scoped read away. |  | Data integrity
ADR-044 | Every call to the 'front door' (webhook) gets a CFG_Request record | Every webhook invocation creates one Requests row, regardless of whether it's an initial provisioning request or a config update. Status field disambiguates the type and outcome. The original ACTIVE row is never overwritten. | Config update webhooks need an audit trail in the Requests table. Options: reuse the existing ACTIVE row (overwriting status), or create a new row. | Config update webhooks create a new Requests row with status = CONFIG_UPDATE, which transitions to CONFIG_APPLIED on success or FAILED on failure. The original ACTIVE row stays ACTIVE untouched. Extended status enum: PENDING ¦ PROVISIONING ¦ CONFIG_UPDATE ¦ CONFIG_APPLIED ¦ ACTIVE ¦ REJECTED ¦ FAILED | Each webhook invocation = one Requests row. The original row's ACTIVE status is the canonical 'this project is live' marker and shouldn't be overwritten. The VER_TemplateVersion chain provides the detailed audit trail of what changed; the Requests row provides the operational audit trail of when and who triggered it. | (1) Reuse the ACTIVE row, overwriting status: Loses historical detail (when did the last update happen? did it succeed?). Mixes lifecycle states (the project is still ACTIVE; only the latest update is CONFIG_UPDATE/APPLIED). (2) Append CONFIG_UPDATE rows but flip the original to a different status: Same loss of canonical 'project is live' marker. | (1) The Requests table grows with every config update, not just every initial provision. (2) The status enum extends to CONFIG_UPDATE, CONFIG_APPLIED, FAILED. (3) Operational queries that count 'active projects' must filter by status = ACTIVE specifically (not 'not REJECTED'). |  | Data integrity, Orchestration
ADR-045 | table_results_map persisted to FileStorage | table_results_map (the mapping of logical table names to Workato table IDs and field UUIDs produced during R-2a provisioning) is serialized to FileStorage and pointed to from the Requests row, so the config-update path can read it without re-running R-2a. | table_results_map is produced by R-2a during provisioning. The config update path (R-1b → R-2b) needs this map but doesn't run R-2a. Without persistence, every config update would have to re-derive table IDs. | R-2a serializes table_results_map to FileStorage after provisioning and stores the file ID on both WFA_TemplateProject and the Requests row. On the update path, R-1b reads it from FileStorage (via the Requests row pointer) and passes it to R-2b. | The map is immutable — table IDs and field UUIDs don't change after provisioning. FileStorage is the established distribution mechanism for frozen data (extends the parsed config pattern from ADR-032). Storing the pointer on the Requests row means R-1b can resolve it without a project lookup. | (1) Store table_results_map as a column on WFA_TemplateProject directly: Data Table cell size limits make this risky for projects with many tables. (2) Re-derive on every update by querying the Workato Data Tables API: Adds N API calls per update. Wasted work on immutable data. | (1) WFA_TemplateProject and Requests both gain a table_results_map_file_id pointer. (2) FileStorage holds one map per project, written once at provisioning. (3) Any future schema-mutating recipe must invalidate or regenerate the map — currently no such recipe exists. |  | Data integrity, Integration
ADR-046 | Existing suppliers unaffected by config updates | When a new config version is published, existing WFA_SupplierRequest rows keep their frozen assigned_version_id and continue validating against the old version. Reassignment to a new version is a separate, explicit analyst action. | When a new config version is published, existing WFA_SupplierRequest rows reference the old version via assigned_version_id. Should they be migrated to the new version automatically? | No automatic migration. Existing suppliers keep their frozen assigned_version_id and continue validating against the old version. Supplier reassignment to a new version is deferred to a future iteration. | A supplier mid-workflow could have their validation rules change out from under them — silent corruption of in-flight work. The safe default is stability — each supplier sees the version they were onboarded with. Reassignment is a conscious analyst action, not an automatic side effect of editing the config workbook. | (1) Auto-migrate all WFA_SupplierRequest rows to the new version on publish: Risk of breaking active supplier workflows. (2) Auto-migrate only 'pending' (untouched) rows: This is the design captured in ADR-039 for the slot/label re-stamp case; AD-29 retains the broader principle that 'beyond pending' is frozen. | (1) Multiple template versions can be active concurrently — V1 for in-flight suppliers, V2 for newly-onboarded ones. (2) Old CFG rows must remain queryable (reinforces ADR-043, version scoping not deletion). (3) Reassignment, when needed, becomes an explicit analyst-triggered action — not yet built. |  | Data integrity
ADR-047 | No incremental supplier bootstrapping on config update | When the analyst adds new suppliers to the config workbook and re-fires the webhook, the update path does NOT create WFA_SupplierRequest rows for them. Adding suppliers requires either re-provisioning or a future dedicated flow. | If the analyst adds new suppliers to the config workbook and re-fires the webhook, should the update path create WFA_SupplierRequest rows for the new suppliers? | No. The update path (R-2b with is_initial=false) does not call R-008. New suppliers added to the config are not bootstrapped on the update path. | Incremental bootstrapping requires diffing the new config against existing supplier rows, handling edge cases (renamed suppliers, removed suppliers, changed user assignments), and deciding what happens to the new suppliers' versions. This is real complexity with real risk. Deferred until the use case is validated by actual analyst requests. | (1) Always call R-008 on update with full diff logic: Significant new design surface for an unvalidated need. (2) Optional flag on the webhook to opt into supplier bootstrapping on update: Pushes complexity onto the caller without solving the diff/edge-case question. | (1) Adding suppliers requires either re-provisioning the project or a future dedicated 'bootstrap incremental suppliers' recipe. (2) The is_initial=false branch in R-2b is deliberately narrow: hydrate config tables, freeze old version, publish new version. Nothing else. (3) Documenting this as an explicit non-decision prevents the obvious 'just re-run R-008' suggestion from quietly being implemented. |  | Orchestration
ADR-048 | Slot-based manual input staging | Suppliers entering worker data manually do so through the pre-provisioned typed slot pool on WFA_SupplierRequest (slot_text_01 ... slot_date_04, etc.) rather than directly editing the RUN_ManualEntry EAV table. WFA-02 maps slot values into RUN_ManualEntry rows on each save. | Suppliers can enter worker data manually via a WFA page (P-002) instead of uploading a file. The original design exposed the raw RUN_ManualEntry EAV table directly as an editable widget. Problems: the EAV table is not a usable input surface, the page lost data on save, and the UX was confusing. | Redesign around the slot fields already present on WFA_SupplierRequest: (1) Slots serve as a clean, dynamic input form. Labels come from CFG_FormSlot. (2) 'Save & add worker' calls WFA-02 (née R-007c) via invoke-app-function, passing slot values as trigger parameters. (3) WFA-02 maps each slot to its field_id via CFG_FormSlot.slot_name, writes rows into RUN_ManualEntry with the correct row_number, returns success. (4) The page clears the form via reset-widgets-values. (5) RUN_ManualEntry table widget stays on the page as a read-only accumulator. (6) A separate 'Submit all' button calls WFA-03 (née R-007b) to trigger validation. | The slot → staging → accumulator pattern separates the input surface (slots, controlled by config) from the storage surface (EAV table, structural). The supplier interacts with a clean form; the complexity is hidden in the recipe. | (1) Dynamically create per-client data tables: Workato Data Tables are design-time artifacts — they can't be created or schema-altered programmatically. Table widgets also require static bindings. (2) One request per worker with slot-only input: Business requirement is multiple workers per supplier request. (3) Direct EAV table editing (status quo): UX is poor; data persistence broke. | (1) WFA-02 (Save worker entry) is now a small, single-purpose recipe. (2) CFG_FormSlot must be hydrated correctly during provisioning — slot↔field mapping is the contract. (3) RUN_ManualEntry remains EAV-shaped, populated one slot-save at a time. |  | Domain model, Integration
ADR-049 | Validation pipeline split into Python pre-processing and SQL | Validation is a two-phase pipeline. Phase 1 is Python pre-processing (constraint parsing, regex evaluation, date normalization, token resolution). Phase 2 is a single SQL query with sixteen CTEs covering all rule types. | The V-01 validation SQL originally implemented only 1 of 17 rule types (conditional_required). Expanding to all 17 within pure SQL is impractical — SQLite lacks regex support, date normalization requires format-aware parsing, and constraint strings (e.g., 'min:1,max:50') need parsing. | Two-phase validation: Phase 1 — Python pre-processing (py_eval step): - Parses constraint strings (field_length_validation → len_min/len_max, numeric_field_validation → numeric_min/numeric_max, date_field_validation → date_min/date_max) - Resolves tokens (today → current date) - Normalizes submitted dates to ISO-8601 (YYYY-MM-DD) based on data_format - Evaluates regex patterns via re.fullmatch() - Outputs: enriched_fields, normalized_payload, precomputed_errors Phase 2 — SQL (16 CTEs): - Single-field: presence_required, presence_must_be_empty, lookup_failures, column_unique_failures, length_failures, numeric_range_failures, date_range_failures - Cross-field: conditional_required, conditional_empty, mutually_exclusive, at_least_one, must_match, must_not_match, comparison (gt/gte/lt/lte), composite_unique - Pre-computed: precomputed_passthrough (regex and date parse errors from Python) | Each phase does what it's good at. Python handles parsing, normalization, and regex. SQL handles set-based comparisons, joins, and cross-row checks. The boundary is clean: Python enriches the inputs, SQL evaluates the rules. | (1) Pure SQL with custom SQLite extensions: Workato's Query Data action doesn't support extension loading. (2) Pure Python row-by-row: Loses set-based efficiency. A 50,000-row submission would be unworkable. (3) External validation service: Adds infrastructure; loses Workato-native execution. | (1) The validation recipe has two heavy steps (py_eval + Query Data) instead of one. (2) The Python step's outputs (enriched_fields, normalized_payload) become a documented intermediate contract. (3) Adding a new rule type means adding one Python parsing branch (if needed), one CTE, and one row in _mapping. |  | Orchestration, Domain model
ADR-050 | Rule keys are backend_error_code, not display names | CFG_Rule.rule stores the canonical machine-readable backend_error_code (e.g., err_conditional_required), not the analyst-facing display name (e.g., 'Required if'). Translation happens in the connector at parse time. | CFG_Rule.rule originally stored display names from the config spreadsheet dropdown ('Required if', 'Must be empty if'). The validation SQL needs machine-readable keys for CTE matching, and display names are unstable (translatable, editable in the spreadsheet). | The canonical rule key is the backend_error_code from the _mapping sheet (e.g., err_conditional_required, err_conditional_empty). The config parser (connector Action 1) translates display name → error code when writing CFG_Rule rows. Analysts continue to use human-readable dropdown labels. | Display names are for humans; code paths need stable, predictable strings. Adding a new rule type means adding one _mapping row — the SQL picks it up via the CTE name, no recipe changes needed. _mapping decouples spreadsheet UX from code identifiers. | (1) Store both display name and code: Two fields where one suffices; either source-of-truth question never gets answered. (2) Hash the display name to derive a key: Stable until someone edits the label, then silent breakage. | (1) The _mapping sheet is part of the canonical config contract. (2) Connector action parse_config does the translation; no other recipe needs to know display names. (3) Validation SQL CTEs are named after backend error codes, providing a one-to-one mapping between rule type and CTE. |  | Domain model, Integration
ADR-051 | customer_name denormalized onto WFA_SupplierRequest | customer_name is a plain short-text field on WFA_SupplierRequest, populated at bootstrap time from WFA_TemplateProject.project_name. It is not a relation column. | Multiple downstream recipes and the supplier-facing WFA page need the client/project name. It lives on WFA_TemplateProject. WFA pages cannot traverse relation columns to display fields from linked tables. | customer_name is a plain short-text field on WFA_SupplierRequest, populated at bootstrap time from WFA_TemplateProject.project_name. Written in P-03 (née S-00) step 12. | project_name is write-once and immutable for the life of a project. No sync risk from denormalizing. Avoids an extra DB lookup in every recipe that needs the name. The WFA page constraint (no relation traversal) makes this practically necessary, not just preferable. | (1) Relation column to WFA_TemplateProject: WFA pages can't traverse relations — you'd still need the text field. (2) Lookup at every read: Adds a DB hit per recipe invocation; doesn't solve the WFA page traversal problem. | (1) WFA_SupplierRequest gains a customer_name short-text column. (2) P-03 step 12 (formerly the bootstrap py_eval in P-01) is the single write site. (3) Extends the spirit of the earlier ADR-022 entry; the implementation point shifted from P-01 py_eval to P-03 step 12 between sessions. |  | Domain model
ADR-052 | Recipe naming convention | Recipe names follow the pattern {phase}_{sequence} {verb} {object}. Phase prefix indicates pipeline stage (B=Bootstrap, P=Provisioning, WFA=app-function-triggered, V=Validation, U=Utility). The legacy R-### codes are mapped to the new names via a canonical translation table. | Recipe names were inconsistent — some used R-### codes, some used descriptive names, some mixed both. The prefix gave no indication of what pipeline phase the recipe belonged to. | Convention: {phase}_{sequence} {verb} {object} Phase prefixes: - B = Bootstrap (base-project provisioning chain) - P = Provisioning (project setup, config, onboarding) - WFA = app-function-triggered (page interactions) - V = Validation pipeline - U = Utility (cross-cutting helpers) Canonical mapping (selected): - C-01 → P-01 Provision project - C-02 → P-02 Build XLSX template - P-02b → P-02b Seed incumbent data - S-00 → P-03 Onboard suppliers - WFA-001 → WFA-01 Advance stage to started - R-007c → WFA-02 Save worker entry - R-007b → WFA-03 Submit manual input - R-6 → WFA-04 Submit file upload - R-7 → V-01 Validate supplier input - R-8 → V-02 Route validation results | Phase prefix tells you where the recipe lives in the pipeline at a glance. Verb-object tells you what it does. Sequence numbers within a phase reflect execution order. Old R-### codes were arbitrary and didn't communicate pipeline position. | (1) Keep R-### codes, add documentation: Documentation drifts; the codes are the names you actually see in Workato. (2) Pure descriptive names without prefixes: Loses the pipeline-position-at-a-glance benefit. | (1) Existing recipe call sites must be updated to the new names (or use Workato's recipe-by-flow-id binding). (2) The convention itself may be considered more of a style guide than an architectural decision; included in ADR for visibility because adherence affects readability of every other ADR. (3) New recipes are expected to follow the convention from creation. |  | Cross-cutting
ADR-053 | Task assignment wired to WFA_SupplierUser, not WFA_SupplierRequest | P-03's human_review_on_existing_record steps assign tasks to user emails sourced from WFA_SupplierUser.user_email, inside the SupplierUser foreach loop, so every invited user receives their own task. | P-03 (née S-00) steps 22–23 assigned tasks using contact_email from WFA_SupplierRequest. That field is never populated — emails exist only on WFA_SupplierUser.user_email. Additionally, both steps were inside the request foreach but outside the user foreach, so only one user per request would ever get a task. | Move steps 22–23 inside the SupplierUser foreach loop. Wire the email pill to WFA_SupplierUser.user_email. Every invited user receives their own task. Multi-user suppliers are supported naturally. | The data model already supports multiple users per supplier request (via WFA_SupplierUser, per ADR-033). The task assignment must follow the same cardinality. | (1) Backfill contact_email from the first user: Doesn't solve the multi-user case; only one user gets a task. (2) Single task per request, multi-recipient: Workato task assignment is single-assignee; would require a custom routing layer. | (1) P-03's foreach nesting is now request → user → assign_task, not request → assign_task. (2) A multi-user supplier results in N tasks, one per user. (3) contact_email on WFA_SupplierRequest may eventually be retired; for now it's left as legacy/diagnostic. |  | Orchestration
ADR-054 | Stage change moved from submission recipe to validation recipe | WFA-03 (Submit manual input) updates the request status to submitted then calls app_function_return. The stage change to 'Validating' is moved into V-01 (the next recipe in the chain), which runs asynchronously after the user task resolves. | WFA-03 (née R-007b) tried to change the workflow stage to 'Validating' before app_function_return resolved the human review task. This failed because app_function_return terminates recipe execution, and the stage change can't happen while the task is still pending. | Reorder: WFA-03 updates the request status to submitted, then calls app_function_return (which terminates the recipe and resolves the task). The stage change to 'Validating' moves into V-01, which runs asynchronously after the task resolves. | app_function_return is a hard stop — nothing executes after it. The status update (a plain data table write) works regardless of task state. The stage change requires the task to be resolved first, so it belongs in the next recipe in the chain. | (1) Reorder steps so stage change precedes app_function_return: Same problem — app_function_return needs to be the last side effect in WFA-03 because of how it terminates. (2) A small intermediate recipe between WFA-03 and V-01: Adds a hop with no business purpose. | (1) V-01 now owns the 'Validating' stage transition as its first action. (2) WFA-03's responsibility ends at status=submitted plus app_function_return. (3) Generalizes to a pattern: stage transitions belong to the recipe that runs after task resolution, not the one that resolves the task. |  | Orchestration
ADR-055 | Three state machines govern the provisioning lifecycle | The SDC platform's lifecycle is governed by three independent state machines, each owned by a different table: HOME_Requests (request lifecycle), VER_TemplateVersion (template version lifecycle), and WFA_SupplierRequest (supplier submission lifecycle). State transitions on each are constrained to a documented set; recipes that update status fields on these tables must respect the documented transitions. | The platform's lifecycle has multiple parallel concerns: a request is provisioned, a template version is published, suppliers submit data. Conflating these into a single status field forces edge cases (a 'submitted' request that's also 'deprecated' has overloaded meaning). Without documented state machines, recipes accumulate ad-hoc transition logic that contradicts itself across recipes. | Three state machines, each owned by one table: (1) HOME_Requests: PENDING → PROVISIONING → ACTIVE ¦ CONFIG_UPDATE → CONFIG_APPLIED ¦ REJECTED ¦ FAILED. (2) VER_TemplateVersion: draft → published → deprecated. (3) WFA_SupplierRequest: pending → in_progress → submitted → validating → corrections_needed ¦ review → complete ¦ canceled. Transitions are documented; recipes must respect them. | Separating the three lifecycles isolates concerns. A version going from published to deprecated doesn't say anything about whether a supplier request is in progress. A supplier submitting data doesn't change the project's request status. Each machine answers one question; trying to encode all three in a single field always produces ambiguity. | (1) Single composite status per row: Combinatorial explosion of states. The 'ACTIVE + draft + pending' state means nothing useful. (2) Implicit states (no status fields, derive from data): Forces every reader to re-derive state from data + history. Slow and error-prone. | (1) Recipes that touch any of the three tables must update status only on documented transitions. (2) A working spreadsheet (per the next ADR) holds the transition tables; ADRs hold the rationale. (3) Drift between the documented machine and recipe behavior is detectable by static analysis; not yet automated. |  | Data integrity, Cross-cutting
ADR-056 | State machines documented in working spreadsheet, not solely in code or ADRs | The state-machine transition tables, phase taxonomy, and other tabular reference data live in a working spreadsheet alongside the ADRs. ADRs hold the why; the spreadsheet holds the what. | State-machine details (legal transitions, permitted callers, terminal states, drift pairs) are tabular by nature and grow as the system grows. Inlining them into ADRs makes the ADRs unwieldy and the data hard to reference. Inlining them into recipe JSON makes them invisible to anyone reviewing architecture. | Maintain a working spreadsheet (Google Sheets) with one tab per state machine and one tab per cross-cutting reference (event phase taxonomy, recipe inventory, etc.). ADRs reference the spreadsheet by name; the spreadsheet is authoritative for tabular data. | Tabular data deserves a tabular tool. Editing a transition table inline in markdown is error-prone; the spreadsheet allows sorting, filtering, and column-level discipline. ADRs become more focused — they explain why the table exists and the principles, not the rows. Diagrams in ADRs (Mermaid, etc.) remain optional illustrations; the spreadsheet is the single source. | (1) Inline tables in ADRs: Hard to edit, hard to reference, scales poorly. (2) Code-as-truth (JSON/YAML schema files): Cleaner for tooling but worse for editing during discussion. Acceptable as an export target but not as the primary author surface. (3) Database table: Overkill for tens of rows. | (1) The spreadsheet must be kept in sync with recipe changes; drift produces a misleading reference. (2) Mitigation: changes to recipes that affect state transitions update the spreadsheet as part of the same change, not in a follow-up. (3) Future automation can mechanically detect drift between documented and actual behavior. |  | Cross-cutting
ADR-057 | Observability through structured event logging, not pub/sub | Observability is a single canonical event table (SYS_EventLog) populated via append-only writes from recipes at meaningful lifecycle moments. Consumers query the log; there is no subscription, dispatcher, or event bus. | The platform needs to surface lifecycle progress to multiple audiences: analysts ('what happened to my request?'), suppliers ('what do I need to do next?'), operators ('what's stuck?'). Without a unified narrative source, each audience must navigate raw data tables, decode UUID-keyed state, and synthesize timelines by eye. The instinct to 'go event-driven' is appealing but solves a different problem (decoupling producers from reactive consumers). | Observability is implemented through structured event logging: - Canonical SYS_EventLog table receives all events. - Every event includes: event_id, timestamp, correlation_id, project_id (optional), analyst_email (optional), supplier_request_id (optional), source_recipe, phase, severity, human_message, details_json. - Recipes emit events at meaningful moments via a single utility recipe (U-01). - Consumers query the log with filters appropriate to their audience. Events are descriptive, not prescriptive. There is no consumer subscription. | A queryable timeline of 'what happened' is what audiences actually need. State alone tells them where things are; the event log tells them how things got there. Pub/sub would add operational complexity (subscriptions, asynchronous chains, consumer lag) for a benefit (decoupling) that doesn't apply — consumers are queries, not reactive workflows. Workato also lacks native event-bus primitives; building them would be substantial work. | (1) Pub/sub event-driven architecture with subscribers: Adds infrastructure complexity for a problem that doesn't need it. (2) Direct logging to Workato job history only: Job history is per-recipe, hard to correlate across recipes, not queryable for analyst-facing narratives. (3) State-only views (no event log): Answers 'where is this now?' but not 'how did it get here?' — and the second is what audiences actually need. (4) Multiple specialized log tables: Fragments the timeline; querying 'what happened to correlation_id X' requires unioning tables. | (1) Recipes accumulate emit calls at lifecycle moments. Roughly one emit per state transition plus a few milestone emits per recipe. (2) The event log grows monotonically. Retention/archival is a future concern. (3) Consumers depend on the event log being current and complete. (4) New consumers (supplier portal, daily digest, LLM narratives) are built against the log, not by subscribing to anything. |  | Cross-cutting
ADR-058 | Event phase taxonomy is canonical and shared across recipes | The phase vocabulary (webhook_received, webhook_validated, version_published, validation_passed, etc.) is a single canonical taxonomy. Recipes use shared phase names where the lifecycle moment is shared. Differentiation between recipes is via source_recipe, not by inventing per-recipe phase names. | Without a shared vocabulary, every recipe invents its own phase names (request_received in B-01, request_arrived in B-05, intake_started in B-06). The event log loses its 'union of timelines' property — each recipe's events live in a private namespace. Shared queries become impossible. | Phase names are canonical. Shared lifecycle moments use shared names (e.g., webhook_received is fired by every intake recipe). Per-recipe specifics live in source_recipe and human_message, not in the phase name. New phases are added deliberately, not ad-hoc, and documented in EVENT_PHASES.md (or the working spreadsheet). | A canonical taxonomy makes the event log queryable as a unified timeline. 'Show me every webhook arrival across all intake recipes today' is a single filter, not a union of N recipe-specific phase names. The discipline costs little (one decision per phase) and pays off every time someone queries the log. | (1) Free-form phase names per recipe: Loses cross-recipe queryability. (2) Phase name encodes recipe (e.g., b01_webhook_received): Reinvents source_recipe. (3) Strictly typed phase enum in code: Workato doesn't enforce string enums; the discipline must be social. | (1) Adding a new intake recipe (B-06, B-07) doesn't add new intake phases — they reuse webhook_received, webhook_validated, etc. (2) Differentiation is via source_recipe and human_message ('Config submission received from emily@…' vs 'Access request received from emily@…'). (3) The phase list is a small, deliberately curated set; growth is intentional. |  | Cross-cutting
ADR-059 | U-01 generalizes from error handler to event emitter | U-01 is a single utility recipe that owns all writes to SYS_EventLog. It accepts a phase, severity, and structured payload, and writes one row. There is no separate E-01 'emit event' utility — severity disambiguates what would otherwise be parallel error/info recipes. | Earlier design considered two utilities: a U-01 'pipeline error handler' and an E-01 'event emitter'. Both write to a similar log shape; both are called from many recipes; both have similar contracts. | Collapse to one utility (U-01) that handles all event emission. The severity field (info ¦ warn ¦ error) disambiguates. Specialized error handling logic (urgency routing, alerting) keys off severity within U-01. | Two utilities with overlapping contracts is one too many. The severity field already encodes the distinction; making it a recipe boundary adds nothing. One emit point also means one place to evolve the event schema. | (1) Separate U-01 (errors) and E-01 (events): More recipes, duplicated emit logic, drift between them. (2) Inline emission in every recipe: Loses the centralized emit point; schema evolution becomes a fan-out problem. | (1) Every recipe that previously called a hypothetical E-01 now calls U-01 with appropriate severity. (2) U-01's name is slightly awkward (it sounds error-specific) but the cost of renaming exceeds the cost of accepting the legacy name. (3) Severity-keyed routing (alert on error, log on info) is centralized in U-01. |  | Cross-cutting
ADR-060 | Generalization criteria for shared recipes | Cross-cutting concerns (event emission, error formatting, path construction) become shared recipes or connector actions. Structurally similar but business-divergent recipes (B-01 config submission vs B-05 access request) stay parallel — same shape, different recipe. | The platform has B-01 (config submission) and B-05 (access request). Both are webhook intake recipes with similar structure (receive, validate, route). The temptation is to extract a shared 'webhook intake' recipe; doing so couples two concerns that diverge after the intake stage. | Extract a shared recipe when: (1) The concern is genuinely cross-cutting (used by N>1 callers for the same purpose). (2) The contract is stable across callers (same input shape, same output shape). (3) Divergence between callers would create maintenance pressure on the shared recipe. Keep parallel implementations when: (1) Recipes look similar but represent different business processes. (2) Callers diverge after the shared portion. (3) The shared portion is small enough that duplication cost < coupling cost. Applied: U-01 is shared (event emission is cross-cutting). B-01 and B-05 stay parallel (structurally similar, business-divergent). | The trap is treating structural similarity as a reason to share code. Two recipes that look the same but mean different things will eventually diverge in the shared portion, and you'll either fork them (defeating the purpose) or accumulate special cases (worse than parallel implementations). Cross-cutting concerns are different — they're the same purpose serving N callers, which is what shared code is for. | (1) Always extract on structural similarity: Leads to over-coupled, special-case-laden shared recipes. (2) Never extract: Misses real wins for cross-cutting concerns like event emission and path construction. | (1) U-01, build_storage_path connector action, error-message construction utilities are shared. (2) B-01 and B-05 are parallel; shared intake phases come from the canonical event taxonomy (ADR-058), not from shared code. (3) Documentation effort shifts: the patterns enforced by convention (event taxonomy, naming) need to be written down so they're consistent across parallel implementations. |  | Cross-cutting

## Sheet9
Title | Description | Date | Promoted to
Task visibility and assignment (S-00) | The WFA task assignment was broken because 'share_request' and 'human_review_on_existing_record' used 'contact_email' from WFA_SupplierRequest. However, the field was never populated because the configuration sheet's '2_suppliers' has no email column (it was moved to '3_users', which is written to 'WFA_SupplierRequest'.user_email). Moved both steps inside the SupplierUser forEach loop and rewired them to 'user_email', so every invited user gets their task. This naturally supports multi-user suppliers. | 2026-04-10 | ADR-053 (was AD-37)
RUN_ManualEntry relation binding (S-00) | The RUN_ManualEntry batch create step in S-00 was missing the supplier_request_id relation field mapping, so rows were being created, but orphaned. The page table widget found nothing to display. We added the relation mapping using the Workato Record ID (not the business UUID), consistent with how relation fields wordk throughout the Workato platform. | 2026-04-10 | Bug fix BF-01 — not promoted to ADR
Slot-based manual input staging | The original design used an EAV table (RUN_ManualEntry) directly on the page for manual input, which was unattractive and difficult to use. We redesigned the flow so the slot fields on WFA_SupplierRequest serve as a reusable input form; the supplier fills in slot fields (with dynamic field labels from CFG_FormSlot), clicks "Save and add worker", which calls a recipe. The recipe reads the slot values from the trigger parameters, maps each slot to its field_id (via CFG_FormSlot.slot_name), and writes the values into RUN_ManualEntry with the correct row number. The page clears the form via 'reset-widgets-values' on the follow-up action. The RUN_ManualEntry table stays on the page as a read-only summary of workers saved so far. A separate "Submit all" button calls another recipe to trigger validation. | 2026-04-10 | ADR-048 (was AD-32)
Task completion ordering | app_function_return' terminates recipe execution in Workato, so the workflow stage change and status update can't run after it. We moved 'status' --> 'submitted' before the return and pushed the stage change to the downstream validation recipe, which runs asynchronously after the task is resolved. | 2026-04-10 | ADR-054 (was AD-38)
Validation pipeline | The validation SQL was implementing just one of the promised validation types. We split the fix into two parts: 1. Python pre-processing Added a new python step between data loading and SQL that parses 'min:X,max:Y' validation strings into discrete columns (len_min, len_max, numeric_min, numeric_max, date_min, date_max), normalizes submitted dates to ISO-8601 based on 'data_format', resolves 'today' tokens into date constraints, and evaluates regex patterns (emitting pre-computed error rows). This keeps the SQL clean and free of string parsing or regex eval in SQLite. 2. SQL expansion Rewrote the SQL with all 16 CTEs covering all rule types. Single-field validations (required, must-be-empty, lookup, column unique, length, numeric range, date range) read from CFG_Field cia the enriched fields source. Complex validations (conditional required, conditional empty, mutually exclusive, at least one required, must match, must not match, four comparison operators, composite unique) read from CFG_Rule using the error_code as the rule key. Pre-computed errors from Python pass through as a 6th source table and merge into the 'all_errors' union. | 2026-04-10 | ADR-049 (was AD-33)
Lookup validation fix | The original lookup CTE used 'json_each(1.valid_values)' assuming each lookup row held a JSON array. CFG_Lookup stores one value per row. We replaced it with a 'NOT EXISTS' subquery that checks across all rows for that 'lookup_name'. | 2026-04-10 | Bug fix — not promoted to ADR
Manual input payload routing | resolved_payload' was only set inside the 'if (file_id present)' branch. For manual input (no file), the variable stayed empty, and the SQL had nothing to validate. We added an else branch to set 'resolved_payload' from the trigger's 'transposed_payload' parameter. | 2026-04-10 | Bug fix BF-02 — not promoted to ADR
Rule key convention | Display names ("Required if") were being stored in 'CFG_Rule.rule', but the SQL needs machine-readable keys. We standardized on using the 'backend_error_code' values from the '_mapping' sheet (err_conditional_required, err_conditional_empty, etc) as the canonical rule keys. A new column was added to '_mapping' to hold these, and the config parser will translate display names to error codes when writing CFG_Rule rows. | 2026-04-10 | ADR-050 (was AD-34)
Data table hygiene | Six fields renamed for clarity: Five stale recipe references in hints were updated. Eighteen missing hints added. Identified dead fields ('valid_payload' on 'RUN_Upload') and deleted. | 2026-04-11 | Schema changes — not promoted to ADR
Recipe naming convention | Standardized on '{phase}_{sequence} {verb} {object} with three phase prefixes: "P" (provisioning), "WFA" (app-function or page triggered), and "V" (validation pipeline). | 2026-04-11 | ADR-052 (was AD-36)
Client name denormalization | Added 'client_name' as a plain 'short-text' field on 'WFA_SupplierRequest', populated at bootstrap from 'WFA_TemplateProject.project_name'. A relation to 'WFA_TemplateProject' was rejected because WFA pages can't traverse relations to display linked fields. Since 'project_name' is write-once, they're no sync risk. | 2026-04-12 | ADR-051 (was AD-35) — extends ADR-022
Seeding is split-and-merge in a single recipe | Context: Incumbent data arrives as a single file containing all suppliers rows. Each supplier only needs their rows, pre-filled into their template XLSX. Decision: One recipe (P-02b) handles both partitioning the incumbent file by supplier and merging each supplier's rows into their template. No intermediate seed files are stored. Rationale: The deprecated 9a (merge) and 9b (ingest) split this across two recipes with intermediate storage. Combining them eliminates a file write per supplier and a recipe handoff. The Python step does the partition and merge in a single pass with Pandas (filter) and openpyxl (write). | 2026-04-13 | Open — consider new ADR if pattern repeats
GAS remains a thin POST layer | Previously GAS handled template generation and could have handled incumbent data splitting. |  | Reaffirms ADR-021

## Sheet7
Number | Name | Description
1 | New client setup | New configuration, new implementation.
2 | Config update | Analyst modifies configuration spreadsheet and submits for re-publishing.
3 | Supplier downloads template | Supplier downloads template (blank or seeded)
4 | Supplier submits file via file upload | Supplier uploads completed XLSX template via WFA
5 | Supplier submits data via manual entry | Supplier provides input using the UI in the WFA.
6 | Analyst reviews and accepts | After programatic validation of a supplier upload, the analyst must review the data and "ACCEPT" or "REJECT"
7 | Outreach reminders | Send follow up emails if a supplier hasn't provided data after reminder_days_1, reminder_days_2, reminder_days_3...
8 | Export to VMS

## _mapping
layer |  | layer_name | layer_descr | decision_example
Architecture |  | System boundary | Who owns what? Where does the responsibility live? | (1) Which system owns which concerns, (2) Where the handoff points are
Configuration |  | Topology | What is the physical layout? Organization, isolation strategy, how things are arranged | (1) Workspace structure, project/folder organization
Domain model |  | Domain model | How do we represent the world? Decsions about entities, relationships, schema, cardinality
Execution |  | Orchestration | How does the work flow? Structure, sequencing, handoff patterns, responsibility, decomposition of work
Infrastructure | Topology | Integration | How do systems talk? Decisions about contracts, payloads, connectors, external dependencies. Covers anything that crosses a boundary defined in System boundary; represents the shape of the communication, not ownership.
Integration |  | Data integrity | How do we prevent drift and ensure traceability?
Provisioning |  | Cross-cutting | Applies to all layers
Security
Storage | Topology
Template
Validation
Versioning | Data integrity