## README
SDC Persona UAT Tracker — v1
Companion to sdc-persona-test-scripts-v1.md. The doc holds the scripts; this workbook records runs and computes the roll-up.
Tab colors
BLUE tabs = input (you type here): Runs, Executions, ProbeResults, Defects. One fact per row; never merge cells.
GREEN tabs = reference registers seeded from the v1 doc: Scripts, Probes. Edit only when the doc changes.
ORANGE tabs = derived, formulas only: RunPlan, Dashboard. Do not type in these except the yellow lever cells.
Workflow per run
1. Runs — add one row per run. The pre-flight card (E1–E5 from the doc) is columns E–I; the Dashboard slices by these answers.
2. RunPlan — pick the run in the yellow cell B1. The sheet lists all 17 scripts and computes: runnable vs GATED (from that run's E2/E4 answers), executions logged, best completion, mean SEQ, probe accuracy. This is the live checklist to drive a session.
3. Executions — one row per script execution (tester, completion U/A/F, duration in minutes, error count, SEQ 1–7).
4. ProbeResults — one row per probe asked, scored 0 / 0.5 / 1 against the key on the Probes sheet.
5. Defects — one row per anomaly. Severity uses full words (Blocker / Major / Minor) rather than the doc's B/M/m because COUNTIFS is case-insensitive and cannot tell M from m.
6. Dashboard — one computed row per run: unaided completion rate, mean and floor SEQ, probe accuracy (with P4 and P5 — the pilot's thesis probes — reported individually), defect counts. Targets in the yellow row 2 are tunable levers; conditional formatting flags misses.
Conventions and limits
Aggregation formulas cover input rows 2–500 (Defects 2–300). Beyond that, extend the ranges.
Derived lookup columns (Executions J, ProbeResults F–G) are pre-filled to row 200; copy the last formula down if you pass it.
Adding a script: append to Scripts, extend the ScriptIDs defined name, add a matching RunPlan row, and widen the Scripts range inside Dashboard column F (scripts covered).
Row 2 of every input sheet is a worked example (run R0-example) so the formulas demonstrably work. Delete those rows before the first real run.
Assumption: one tester per execution row; a re-run of the same script in the same run is a second row, and RunPlan shows the best completion achieved (U beats A beats F).

## Runs
run_id | date | build / tag | coordinator | E1 mode | E2 Q1(b) fix live? | E3 WFA-013 fix live? | E4 seed gate built? | E5 reminders built? | notes
R0-example | 2026-07-22 | v121-pilot | Emily | pilot | no | no | no | no | Example row — delete before first real run

## Scripts
script_id | persona | title | what it isolates | probes | expectation depends on | requires E2 | requires E4 | hazard | chained from
S-01 | Supplier | Invitation receipt and orientation | Whether the invitation alone orients a cold supplier: the ask, the template, the portal | P1, P2
S-02 | Supplier | Template comprehension and data entry | The template as a self-explanatory instrument: banner, locking, dropdowns, dependent dropdowns, formats
S-03 | Supplier | First submission (clean file) | Upload path end-to-end from the supplier's chair; post-submit messaging; pipeline latency | P3
S-04 | Supplier | Status comprehension and information exposure | Pilot neutrality: blind two-request comparison — supplier must not distinguish passed from failed | P4 | E3
S-05 | Supplier | Rework loop (analyst-initiated) | Only pilot path into SAR: notice the rework, understand the note, correct, resubmit | P5 |  |  |  |  | A-04
S-06 | Supplier | Still-failing resubmission from rework | The Q1(b) path: failed resubmission from supplier_action_required must not stall |  |  | Y |  | Y | A-04
S-07 | Supplier | Approval and terminal comprehension | Closure: supplier knows they are done and stops checking; no residual calls-to-action | P6 |  |  |  |  | A-02
S-08 | Supplier | Bad-file submission (structural path) | Graceful handling of natural wrong files: unmodified template, wrong type, wrong spreadsheet | P7 | E1 mode
S-09 | Supplier | Expired template link (known-gap probe) | Documents the 10-day TTL failure experience ahead of the Workflow 7 build; not pass/fail |  | E5
A-01 | Analyst | Queue discovery and triage | The dashboard's first question — what needs me right now — answered accurately at a glance | P8 | E1 mode
A-02 | Analyst | Review and approve a clean submission | Happy-path decision with a consistent world after: state, approved snapshot, note, history
A-03 | Analyst | Review a failed submission | The pilot's asymmetry: analyst sees verdict, counts, and line errors the supplier must not | P9, P10 | E1 mode
A-04 | Analyst | Request rework with a note | The analyst-to-supplier handoff; the note written here keys the supplier's P5 probe
A-05 | Analyst | Full-cycle history integrity | After rework, resubmit, approve: the record tells the whole story, incl. which file was approved | P11 |  |  |  |  | A-04, S-05, A-02
A-06 | Analyst | Seeded-data review gate | PII gate: approval binds to bytes; invitation blocked with zero side effects; reseed voids approval | P12 |  |  | Y
A-07 | Analyst | Validation report actionability | The report artifact alone: every error translatable into a supplier-fixable instruction | P13
A-08 | Analyst | Guard behavior on out-of-order actions | System manners at the wrong time: refusal with a reason, no partial writes, no silent no-ops

## Probes
probe_id | script_id | question (asked before any coordinator info) | answer key / scoring basis | thesis-critical
P1 | S-01 | In one sentence, what are you being asked to do, and by when? | Matches the invitation's actual ask and deadline
P2 | S-01 | What status does the portal show, and what does it mean you should do? | Reflects the 'sent' derivation: action is with the supplier — complete and submit
P3 | S-03 | What happens next? Do you need to do anything? | Nothing — it's with them now (under review)
P4 | S-04 | Per request: did it pass or fail their checks? How can you tell? | Cannot tell — both requests read identically (score 0 if the tester distinguishes them) | Y
P5 | S-05 | What went wrong, and what exactly do you need to change? | Scored against the specific rework note staged in A-04 | Y
P6 | S-07 | Is there anything left for you to do on this request — now or later? | No — complete
P7 | S-08 | Per bad file: did that work? What should you do now? | Tester correctly infers their next move from the surfaced outcome
P8 | A-01 | How many items need your action right now? Which ones? | Pilot: 2 (both pending_review). Default mode: 1 (failed items auto-returned)
P9 | A-03 | Did this submission pass the automated checks? How many problems were found? | Failed; count matches the coordinator's planted-error key
P10 | A-03 | Would you approve this, or send it back? Why? | Rework, citing at least one planted error specifically
P11 | A-05 | Reconstruct what happened on this request, in order, with dates. | Matches the coordinator's staged timeline: both submissions, both decisions, right order
P12 | A-06 | How many seeded requests await review, and what was seeded into each? | Exactly the staged pending item (control absent); manifest summary read without opening the file
P13 | A-07 | Are any errors ones the supplier couldn't fix from your description alone? | Every planted error yields an actionable instruction; inexplicable ones logged as catalog gaps

## Executions
exec_id | run_id | script_id | tester | date | completion (U/A/F) | duration (min) | errors | SEQ (1-7) | persona (auto) | notes
EX-001 | R0-example | S-01 | T. Tester | 2026-07-22 | U | 6.5 | 1 | 6 | Supplier | Example row — delete before first real run

## ProbeResults
run_id | probe_id | tester | score (0/0.5/1) | evidence / tester's answer | script (auto) | critical (auto)
R0-example | P1 | T. Tester | 1 | Stated the ask and deadline correctly (example) | S-01
R0-example | P2 | T. Tester | 0.5 | Knew the action was theirs; missed the deadline (example) | S-01

## Defects
defect_id | run_id | script_id | step | description | severity | tag | status
D-001 | R0-example | S-01 | 3 | Template link needed two clicks; first opened a preview with no download control (example row — delete) | Minor |  | open

## RunPlan
Selected run: | R0-example
Mode: | pilot | E2 fix: | no | E3 fix: | no | E4 gate: | no | E5: | no
script_id | persona | title | runnable? | executions | best completion | mean SEQ | probe accuracy | hazard
S-01 | Supplier | Invitation receipt and orientation | runnable | 1 | U | 6 | 75%
S-02 | Supplier | Template comprehension and data entry | runnable | 0 | pending |  | —
S-03 | Supplier | First submission (clean file) | runnable | 0 | pending |  | —
S-04 | Supplier | Status comprehension and information exposure | runnable | 0 | pending |  | —
S-05 | Supplier | Rework loop (analyst-initiated) | runnable | 0 | pending |  | —
S-06 | Supplier | Still-failing resubmission from rework | GATED | 0 | pending |  | — | HAZARD
S-07 | Supplier | Approval and terminal comprehension | runnable | 0 | pending |  | —
S-08 | Supplier | Bad-file submission (structural path) | runnable | 0 | pending |  | —
S-09 | Supplier | Expired template link (known-gap probe) | runnable | 0 | pending |  | —
A-01 | Analyst | Queue discovery and triage | runnable | 0 | pending |  | —
A-02 | Analyst | Review and approve a clean submission | runnable | 0 | pending |  | —
A-03 | Analyst | Review a failed submission | runnable | 0 | pending |  | —
A-04 | Analyst | Request rework with a note | runnable | 0 | pending |  | —
A-05 | Analyst | Full-cycle history integrity | runnable | 0 | pending |  | —
A-06 | Analyst | Seeded-data review gate | GATED | 0 | pending |  | —
A-07 | Analyst | Validation report actionability | runnable | 0 | pending |  | —
A-08 | Analyst | Guard behavior on out-of-order actions | runnable | 0 | pending |  | —

## Dashboard
Per-run roll-up — one row per run; compare rows to compare builds
Targets (tunable): | [5 empty] | 80% | 5.5 | 5.5 | 90% | 90% | 90% | 0
run_id | date | build / tag | mode | executions | scripts covered | unaided rate | mean SEQ | floor SEQ | probe accuracy | P4 (no-leak) | P5 (handoff) | Blockers | Majors | Minors
R0-example | 2026-07-22 | v121-pilot | pilot | 1 | 1 | 100% | 6 | 6 | 75% | — | — | 0 | 0 | 1